## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | Admin Registration | As an admin, I want to open admin registration page and save the entered admin details. | Task#1 | Project setup and configuration and access to Login/Registration Page | High | Shrey | 18/3/2019 | 19/3/2019 | 1 |  | Done
|  |  |  | Task#2 | Create Login JSP page | High | Shrey | 19/3/2019 | 20/3/2019 | 1 |  | Done
|  |  |  | Task#3 | Field Validations on Login JSP | Medium | Deepankar | 20/3/2019 | 21/3/2019 | 2 |  | Done
|  |  |  | Task#4 | Create a Registration JSP page to accept the data from Admin as per the field of Login table. | High | Punit | 21/3/19 | 22/3/19 | 2 |  | Done
|  |  |  | Task#5 | Create Login class, Login DAO and Login Service class to insert the admin data and controller and verify on backend. | High | Punit | 22/3/19 | 23/3/19 | 1 |  | Done
|  |  |  | Task#6 | Integrate the code and verify its working . | High | Deepankar | 24/3/19 | 24/3/19 | 1 |  | Done
| #2 | Admin Authentication | As an admin, I want to enter the details for log-in and the credentials get authenticated. | Task#7 | Create the Authenticate function in Login dao , Login service and call the function in the Login controller. | High | Shrey | 25/3/19 | 31/3/19 | 2 |  | Done
| #3 | Add Inventory | As an admin, I want to add the details of inventory and get redirected to the "viewInventory" page. | Task#11 | Create addInventory JSP page to enter the details of inventory. | High | Deepankar | 2019-01-04 | 2019-01-04 | 2 |  | Done
|  |  |  | Task#12 | Field Validations on addInventory JSP page. | High | Punit | 2019-02-04 | 2019-02-04 | 1 |  | Done
|  |  |  | Task#13 | Create viewInventory JSP page. | High | Shrey | 2019-03-04 | 2019-03-04 | 1 |  | Done
|  |  |  | Task#14 | Create Inventory class, Inventory dao and Inventory Service class to insert the inventory data and controller and verify on backend. | High | Shrey | 2019-04-04 | 2019-04-04 | 1 |  | Done
|  |  |  | Task#15 | Integrate the code and verify its working . | High | Deepankar | 2019-05-03 | 2019-05-03 | 2 |  | Done
| #4 | Add Restaurant Staff | As an admin, I want to add the details of staff and get redirected to the "viewStaff" page. | Task#16 | Create addStaff JSP page to enter the details of staff. | High | Punit | 2019-06-04 | 2019-06-04 | 2 |  | Done
|  |  |  | Task#17 | Field Validations on addStaff JSP page. | High | Punit | 2019-07-04 | 2019-07-04 | 1 |  | Done
|  |  |  | Task#18 | Create viewStaff JSP page. | High | Deepankar | 2019-08-04 | 2019-08-04 | 2 |  | Done
|  |  |  | Task#19 | Create Staff class, Staff dao and Staff Service class to insert the staff data and controller and verify on backend. | High | Deepankar | 2019-09-04 | 2019-09-04 | 2 |  | Done
|  |  |  | Task#20 | Integrate the code and verify its working . | High | Shrey | 2019-10-04 | 2019-10-04 | 2 |  | Done
[10 empty] | 1 |  | Done
[10 empty] | 1 |  | Done
| #5 | Inventory Maintenance | As an admin, I want to see the data of the inventory and edit the detaills. | Task#23 | Add function to fetch the data from the database in Inventory dao,call the function in the service and call the service in the inventory controller. | High | Shrey | 2019-11-04 | 13/4/19 | 2 |  | Done
|  |  |  | Task#24 | Add function to update the data in the database in Inventory dao,call the function in the service and call the service in the inventory controller. | Medium | Deepankar | 13/4/19 | 15/4/19 | 3 |  | Done